## RAID
RAID |  | PMO Pack
Double click on the text of RAID to jump to the table
Version 1.0 |  | 2026-01-26

## RISK
RISK
Risk ID | Risk Description | Probability | Impact | Owner | Mitigation Plan | Target Date | Status
R1 | Limited development capacity with only two developers may delay delivery. | Medium | High | Priya (PM) | Prioritize MVP scope; defer non-critical features to Phase 2; monitor workload each sprint. | 2025-03-15 | Open
R2 | Requirements changes late in the project could cause scope creep and rework. | Medium | High | James (PO) | Formalize sign-off on requirements; use simple change control; assess impact before accepting. | 2025-02-28 | Monitoring
R3 | Data migration issues could lead to missing or inconsistent historical records. | Medium | High | Khush (BA) | Run trial migrations; define mapping rules; validate samples with programs team before go-live. | 2025-04-01 | Open
R4 | Low adoption by reviewers due to resistance to changing from email to portal. | Medium | Medium | James (PO) | Provide training, quick guides; run a pilot with a small reviewer group and incorporate feedback. | 2025-04-15 | Open

## Assumptions
Assumptions
Assumption ID | Assumption Description | Owner | Date Logged | Impact if False | Status | Notes
A1 | Two developers will be available for the full duration of the project. | Priya (PM) | 2025-01-10 | High | Valid | Confirmed with IT resource manager.
A2 | Existing scholarship data is sufficiently clean to migrate with light cleansing only. | Khush (BA) | 2025-01-10 | High | At Risk | Data profiling planned in early design phase.
A3 | Applicants and reviewers have reliable internet access and basic digital literacy. | James (PO) | 2025-01-10 | Medium | Valid | Based on prior online survey results.
A4 | Sponsor will approve key decisions within 5 working days of submission. | Olivia | 2025-01-10 | Medium | Valid | Escalation path agreed if decisions are delayed.

## Issues
Issues
Issue ID | Issue Description | Severity | Blocker? | Owner | Action / Resolution Plan | ETA | Status
I1 | Delay in receiving final scholarship criteria from programs team. | High | Yes | James (PO) | Schedule working session; confirm MVP criteria; get written sign-off from sponsor. | 2025-01-25 | In Progress
I2 | Initial UX mockups not accessible for screen-reader users. | Medium | No | Khush (BA) | Review accessibility guidelines; update designs; verify with IT/Security rep. | 2025-02-05 | Open
I3 | Test environment not fully configured, blocking end-to-end testing. | High | Yes | Dev Team | Coordinate with IT to finalize environment setup; add to weekly risk/issue review. | 2025-02-01 | Open

## Decision
Decision
Decision ID | Date | Decision Summary | Rationale | Approver | Impact / Notes
D1 | 2025-01-12 | Proceed with in-house development using existing tech stack. | Internal capability available; lower cost vs vendor; better control. | Sponsor (Olivia) | Confirms dev team ownership; no RFP/vendor selection needed.
D2 | 2025-01-20 | Deliver core MVP portal first; advanced analytics deferred to Phase 2. | Reduce complexity, hit next scholarship cycle, manage with 2 devs. | Sponsor & PO | Scope locked for MVP; analytics added to backlog as Phase 2.
D3 | 2025-02-05 | Use standard single sign-on approach for reviewers and staff only. | Faster implementation and simpler security model for initial release. | IT/Security Rep | Applicants use email-based accounts; SSO for internal users.