## Dependency Tracker
Dependency ID | Dependency Description | Type (Team/Vendor/Content/Legal/Data) | Owner | Due Date | Status (Not started/In progress/Blocked/Done) | Risk if Late | Mitigation
D-01 | Final scholarship program rules and eligibility confirmed | Content | James (Product Owner) | 2025-01-25 | In progress | Application forms and logic cannot be finalized; delays design and build start. | Schedule working session with programs team; escalate to Sponsor if not signed off by due date.
D-02 | Test environment provisioned with required access | Team | IT Infrastructure | 2025-02-01 | Not started | End-to-end testing and UAT are delayed; potential impact on go-live date. | Flag in weekly risk review; agree backup plan (reduced scope test) if environment is late.
D-03 | Extract of historical applicant data for migration | Data | Programs + IT | 2025-02-15 | Not started | Migration tasks slip; limited data available to validate reports and workflows. | Start with sample extract; define minimum data set; plan staged migration if needed.
D-04 | Security & privacy review of portal design and data handling | Legal | IT/Security Rep | 2025-02-20 | In progress | Go-live may be blocked due to non-compliance with security/privacy policies. | Share designs early; book formal security review; track actions in RAID log until closed.
D-05 | Training materials for reviewers, staff, and support prepared | Content | Alex (BA) | 2025-03-10 | Not started | Poor adoption, more support tickets, and confusion at launch. | Draft templates early; review with Product Owner; finalize 2 weeks before training sessions.